## Sheet2
PROGRESS TRACK
Use the following colour coding for showing progress |  |  |  | Task complete | Ongoing | Blocked
|  |  | 2026-03-09 |  |  | 2026-03-10 |  |  | 2026-03-11 |  |  | 2026-03-12 |  |  | 2026-03-13 |  |  | 2026-03-14 |  |  | 2026-03-15 |  |  | 2026-03-16 |  |  | 2026-03-17 |  |  | 2026-03-18 |  |  | 2026-03-19 |  |  | 2026-03-20 |  |  | 2026-03-21 |  |  | 2026-03-22 |  |  | 2026-03-23 |  |  | 2026-03-24
NAME | GIT IDS | MODULE | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID | PROGRESS | COMMENTS | TASK ID
Dibya Pratim Kashyap
Abhay D Parmar | lvl1ralts | Faculty Module | 1 |  | Joined notion workspace and Filled information about preferences and experience. | 2 |  | Logging Setup | 3 |  | Understanding Project | 3 |  | Understood the Project | 3 |  | Understood the Project | 4 |  | Faculty Discussion | 4 |  | Faculty Discussion, Had an online meet and discussed about our module and distributed work, on who will design schema and uml | 4 |  | Faculty Discussion, Distributed the work and I wanted to work on the schema so I did the schema design | 5 |  | Faculty Schema, online meeting for db design | 15 |  | Looked up existing portals so i could get an idea for the db design | 5 |  | Faculty schema, after researching i gave my inputs and we designed the schema on a meet | 5 |  | Faculty Schema | 14 |  | UML Refinement | 14 |  | UML Refinement | 14 |  | UML Refinement
Abhishek Kumar | kumarabhishek1004 | Student module | 1 |  | Onboarding Setup | 2 |  | Logging Setup | 3 |  | Notion | 3 |  | Understood the Project | 3 |  | Understood the Project | 8 |  | Hostel Discussion | 8 |  | Hostel Discussion | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals |  |  | Research Existing Forms and Portals |  |  | Hostel Schema |  |  | Hostel Schema |  |  | Students Planning |  |  | Students Planning
Akshay Bobbala | AkshayB1911 | Faculty Module |  |  |  | 1 |  | filled in the preference form and joined notion workspace | 1 |  | notion | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 4 |  | Faculty Discussion | 4 |  | Faculty Discussion | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema
Annigandla Kameshwara Rao | AnnigandlaKameshwaraRao | Faculty Module | 1 |  | Onboarding setup | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 4 |  | Faculty Discussion | 4 |  | Faculty Discussion | 4 |  | Faculty Discussion | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 10 |  | Module Reallocation | 14 |  | UML Refinement
Anubhav Saha | AnubhavSaha2006 | Hostel Management Page team | 1 |  | Onboarding setup | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 8 |  | Hostel Discussion | 8 |  | Hostel Discussion | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 9 |  | Hostel Schema | 9 |  | Hostel Schema | 14 |  | UML Refinement | 14 |  | UML Refinement
Arsh Chand | ArshChand | Hostel Management Page team | 1 |  | Onboarding setup | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding |  |  |  | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 9 |  | Hostel Schema | 9 |  | Hostel Schema | 3 |  | looked upon uml in general | 14 |  | UML Refinement
Aryashi Tripathi | t-aryashi |  | 1 |  | Onboarding setup | 1 |  | Filled in the preference form and joined notion workspace | 1 |  | notion + git | 1 |  | PS & meet with leads | 1 |  | Meet with leads | 6 |  | Admin view meet | 7 |  | DB design ongoing. Need to discuss with other teams & decide on final DB. After that will work on making the DB on MySQL | 6 |  | Admin Discussion | 14 |  | UML done partly | 14 |  | Met PK Das Sir for UML verification | 14 |  | Refining UML | 14 |  | Refining UML | 10 |  | Module Reallocation | 15 |  | Researching existing stuff
Baswa Dhanush Sai | dhanushsai2006 | Faculty Module | 1 |  | Onboarding setup | 1 |  | filled in the preference form and joined notion workspace | 1 |  | notion | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 4 |  | Faculty Discussion | 4 |  | Faculty Discussion | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema
Bhavya Negi | doesthiseverend | Admin Page Team | 1 |  | Onboarding setup | 1 |  | Filled the Preference form | 1 |  | notion | 1 |  | PS | 1 |  | meet | 3 |  | Project understand | 3 |  | DB design ongoing | 4 |  | Faculty discussion | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 10 |  | module reallocate | 14 |  | UML Refinement
Budumuru Khyathi | khyathi156 | Faculty Module |  |  |  | 1 |  | Filled the Preference form | 1 |  | notion | 1 |  | git | 3 |  | Project Understanding | 4 |  | Faculty Discussion | 3 |  | PS reread |  |  |  | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 14 |  | looked into uml diagrams | 14 |  | looked into uml diagrams
Choudary Srinivas Srikar | Srikar-git1 | Faculty Module | 1 |  | Onboarding Setup | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 4 |  | Faculty Discussion | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 14 |  | UML refinement | 14 |  | UML Refinement
Dengada Dhruv Jitendra | itsmfdhruv | Faculty Module | 1 |  | Onboarding Setup | 1 |  | Filled the Preference | 1 |  | notion | 3 |  | Project Understand | 3 |  | Project Understand | 4 |  | Faculty Discussion | 4 |  | Faculty Discussion | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 14 |  | looked into uml diagrams and understand them | 14 |  | looking into UML diagrams to understand them
Doma Gowtham Reddy | doma2542 | Faculty Module | 1 |  | Onboarding setup | 1 |  | Filled the Preference form | 1 |  | notion | 1 |  | git | 1 |  | Read problem statement clearly | 2 |  | online meet | 2 |  | understanding of the project database | 2 |  | research about existing similar schemas | 2 |  | Faculty Schema | 2 |  | Faculty Schema | 2 |  | Faculty Schema | 2 |  | Faculty Schema | 2 |  | have looked onto the uml part | 2 |  | understood the updated problem statement
Girish M Bhajantri | giri7b | Students Module | 1 |  | Onboarding Setup | 2 |  | Logging Setup | 3 |  | notion + git | 3 |  | Project Understanding | 3 |  | ps reread | 4 |  | Online meet for db design | 4 |  | DB design ongoing. Need to discuss with other teams & decide on final DB. After that will work on making the DB on MySQL | 4 |  | schema attribute changes | 4 |  | finalized attributes | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema
Gunje Manideep Ram | Manideep-Ram-Gunje | Faculty Module | 1 |  | Onboarding setup | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 4 |  | Faculty Discussion | 4 |  | Faculty Discussion | 4 |  | Faculty Discussion | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 10 |  | Module Reallocation | 14 |  | UML Refinement
Hemang Gautam | HemangGautam08 | Students Module | [5 empty] | Filled in the preference form and joined notion workspace
Jayant Kumar | Jayantsikar | Hostel Managment Page team | 1 |  | Onboarding setup | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 8 |  | Hostel Discussion | 8 |  | Hostel Discussion | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 9 |  | Hostel Schema | 9 |  | Hostel Schema | 14 |  | UML Refinement | 14 |  | UML Refinement
Kavya Choudhary | KavyaC11 | Admin Page Team |  |  |  | 1 |  | Filled in the preference form and joined notion workspace | 1 |  | notion + git | 1 |  | ps read | 1 |  | ps reread |  |  | admin meet + db design |  |  | schema drafting |  |  | schema attribute changes |  |  | informed student side dependencies | [5 empty] | ps scope change |  |  | understanding shared UML file | 10 |  | understood shared UML | 11
Krish Randar | KrishRandar | Hostel Managment Page team | 1 |  | Onboarding setup | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 8 |  | Hostel Discussion | 8 |  | Hostel Discussion | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 9 |  | Hostel Schema | 9 |  | Hostel Schema | 14 |  | UML Refinement | 14 |  | UML Refinement
Lasya Madhu Sundar | L-a25 | admin + student design + roles |  |  |  | 1 |  | skills form | 1 |  | notion + git | 1 |  | ps 1st read | 1 |  | ps reread+ insti portal analysis | 3 |  | admin meet + db design | 3 |  | schema drafting, some stuff has tbe discussed cross teams. also yay intermediate doc! : https://docs.google.com/document/d/1u8g0M9RGvpJ4ybeygyQhplGdGrrvWVw68x9hamxGsTE/edit?usp=sharing | 3 |  | schema attribute changes | 3 |  | informed student side dependencies | 3 |  | db schema design, documented tables | NA |  | ps scope changed | 3 |  | reviewed new ps | 3 |  | initial look @ uml, tb reviewed | 3 |  | del extra feature db tables as ps scope enlarged + to comm w new teams to finalize schema | 14 |  | uml refinement
Mamidi Poojitha | PoojithaMamidi-4 | Faculty Module |  |  |  | 1 |  | Filled the Preference form | 1 |  | notion | 1 |  | git | 3 |  | Project Understanding | 4 |  | Faculty Discussion | 3 |  | PS reread |  |  |  | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 14 |  | looked into uml diagrams | 14 |  | looked into uml diagrams
Samar Warsi | warsi1507 | Hostel Management Page team | 1 |  | Onboarding setup | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 8 |  | Hostel Discussion | 8 |  | Hostel Discussion | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 9 |  | Hostel Schema | 9 |  | Hostel Schema | 14 |  | UML Refinement | 14 |  | UML Refinement
Moksh Malhotra | moksh-malhotra | Students Module | 1 |  | Onboarding Setup Completed | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 8 |  | Hostel Discussion | 8 |  | Hostel Discussion | 15 |  | Research existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 9 |  | Hostel Schema | 9 |  | Hostel Schema | 11 |  | Students Planning | 12 |  | Students Planning
Pansuriya Dhruvkumar Rasikbhai | DhruvPansuriya | Admin DB design | 1 |  | Onboarding setup | 1 |  | Filled in the preference form and joined notion workspace | 2 |  | notion + git | 3 |  | ps 1st read | 4 |  | ps reread | 5 |  | admin meet + db design | 6 |  | schema drafting, some stuff has tbe discussed cross teams,Visualized Schema in dbdiagram.io. also yay intermediate doc! : https://docs.google.com/document/d/1u8g0M9RGvpJ4ybeygyQhplGdGrrvWVw68x9hamxGsTE/edit?usp=sharing | 7 |  | Removal of extra Attributes and table and more refinement |  |  | informed student side dependencies | ---- |  | ---- | NA |  | ps scope changed | 14 |  | understanding shared UML file | 14 |  | understood shared UML file + changes | 7 |  | del extra feature db tables as ps scope enlarged + to comm w new teams reg sch to finalize schema
Pinjala Narmada | narmada295 | Admin Page Team | 1 |  | Onboarding setup | 1 |  | Filled in the preference form and joined notion workspace | 2 |  | notion + git | 3 |  | ps 1st read | 3 |  | ps reread | 6 |  | admin meet + db design | 7 |  | schema drafting | 7 |  | removal of extra attributes and further refinements | 10 |  | informed student side dependencies | - |  | - | NA |  | ps scope change | 14 |  | understanding shared UML file | 14 |  | understood shared UML file | 7 |  | del extra feature db tables | -
Pranjal | PranjalKhatri | Admin DB design | 1 |  | Onboarding setup | 1 |  | Filled in the preference form and joined notion workspace | 2 |  | notion + git | 3 |  | ps 1st read | 4 |  | ps reread | 5 |  | admin meet + db design | 6 |  | schema drafting, some stuff has tbe discussed cross teams,Visualized Schema in dbdiagram.io. also yay intermediate doc! : https://docs.google.com/document/d/1u8g0M9RGvpJ4ybeygyQhplGdGrrvWVw68x9hamxGsTE/edit?usp=sharing | 7 |  | Removal of extra Attributes and table and more refinement |  |  | informed student side dependencies | ---- |  | ---- | NA |  | ps scope changed | 14 |  | understanding shared UML file | 14 |  | understood shared UML file + changes | 7 |  | del extra feature db tables as ps scope enlarged + to comm w new teams reg sch to finalize schema
Priyanshu Mondal
Purab Kumar Agarwal | PurabA
Samudrala Manish Kumar | Manish-0914 | Admin DB design | 1 |  | onboarding setup | 1 |  | Filled in the preference form and joined notion workspace | 2 |  | notion + git | 3 |  | ps 1st read | 3 |  | ps reread | 6 |  | admin meet+ db design | 7 |  | schema drafting, some stuff has tbe discussed cross teams,Visualized Schema in dbdiagram.io. also yay intermediate doc! : https://docs.google.com/document/d/1u8g0M9RGvpJ4ybeygyQhplGdGrrvWVw68x9hamxGsTE/edit?usp=sharing | 7 |  | Removal of extra Attributes and table and more refinement |  |  | informed student side dependencies | -- |  | -- | NA |  | ps scope changed | 14 |  | understanding shared UML file | 14 |  | understood shared UML file + changes | 7 |  | del extra feature db tables as ps scope enlarged + to comm w new teams reg sch to finalize schema
Seella Mythresh Babu | mythresh1826 | faculty page module | 1 |  | Onboarding setup | 1 |  | Filled in the preference form and joined notion workspace | 2 |  | notion+git | 3 |  | PS analysis | 3 |  | Analyzed GitHub repos implementing faculty modules | 4 |  | Online meet for db design | 3 |  | project understanding | 4 |  | faculty discussion | 4 |  | faculty discussion | 4 |  | faculty discussion | 5 |  | faculty schema | 5 |  | faculty schema | 5 |  | faculty schema | 5 |  | faculty schema
Freya Mitulbhai Shingala | Freyashingala | Students Module | 1 |  | Onboarding setup | 1 |  | Filled in the preference form and joined notion workspace | 1 |  | notion + git | 1 |  | ps read | 1 |  | ps reread | 4 |  | online meet | 2 |  | schema design | 2 |  | schema design | 2 |  | schema design | 2 |  | db schema design | N/A |  | ps scope changed | 2 |  | understanding shared uml | 2 |  | understanding shared uml | N/A |  | assigned students module
Sunil | Sunil-Yadav7 | Students Module | 1 |  | Onboarding setup | 2 |  | Logging setup and joined notion workforce | 3 |  | notion + git | 3 |  | git and PS read | 15 |  | analysed currently working erp portal | 4 |  | online meet + discussion | 5 |  | schema design | 5 |  | cross checked schema design | 5 |  | finalized attributes | 5 |  | db schema design | 10 |  | ps scope changed | 14 |  | understanding shared UML file | 10 |  | Module Reallocation | 10 |  | analysed the module tasks
Sunki Nagarjun Reddy
Tedla Mahaswin | mahaswint | Admin Page Team | 1 |  | Onboarding setup | 1 |  | Filled in the preference form and joined notion workspace | 1 |  | notion+git | 1 |  | ps 1st read | 1 |  | Talked to the leads to understand my role | 6 |  | admin meet+ db design | 7 |  | DB design | 7 |  | removal of extra attributes and table | 10 |  | informed student side dependencies | 7 |  | Looked into possible refinements | 3 |  | ps scope changing | 14 |  | understanding shared UML file | 14 |  | understood shared UML file + changes | 7 |  | del extra feature db tables as ps scope enlarged
Toshit Jain | toshit3q34 | Admin Page Team | 1 |  | Onboarding setup | 1 |  | Filled in the preference form and joined notion workspace | 1 |  | notion + git | 1 |  | PS & meet with leads | 1 |  | Meet with leads | 6 |  | Admin view meet | 7 |  | DB design ongoing. Need to discuss with other teams & decide on final DB. After that will work on making the DB on MySQL | 6 |  | Admin Discussion | 14 |  | UML done partly | 14 |  | Met PK Das Sir for UML verification | 14 |  | Refining UML | 14 |  | Refining UML | 10 |  | Module Reallocation | 15 |  | Researching existing stuff
Vagisha Shrivastava | vagisha-11 | Hostel Management Page team | 1 |  | Onboarding setup | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 8 |  | Hostel Discussion | 8 |  | Hostel Discussion | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 9 |  | Hostel Schema | 9 |  | Hostel Schema | 14 |  | UML Refinement | 14 |  | UML Refinement
Varri Homa Pramod | pramodh567
Kartik Maheshwari | kartik-2005 | Faculty Page Module | 1 |  | Onboarding setup | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 4 |  | Faculty Discussion | 4 |  | Faculty Discussion | 4 |  | Faculty Discussion | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 14 |  | UML Refinement | 14 |  | UML Refinement
Tushay Gupta | Skidzomaniac | Faculty Page Module | 1 |  | Onboarding setup | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 4 |  | Faculty Discussion | 4 |  | Faculty Discussion | 4 |  | Faculty Discussion | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 5 |  | Faculty Schema | 14 |  | UML Refinement | 14 |  | UML Refinement
Vansh Panwar | Melange-Lf | Hostel Managment Page team | 1 |  | Onboarding setup | 2 |  | Logging Setup | 3 |  | Project Understanding | 3 |  | Project Understanding | 3 |  | Project Understanding | 8 |  | Hostel Discussion | 8 |  | Hostel Discussion | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 9 |  | Hostel Schema | 9 |  | Hostel Schema | 14 |  | UML Refinement | 14 |  | UML Refinement
Parv Goyal | goyalparv | Hostel Management Page team |  |  |  | 1 |  | Joined notion workspace and Filled information about preferences and experience. | 4 |  | Reading complaint forms and Research | 4 |  | Reading complaint forms and Research | 4 |  | Project Understanding | 4 |  | Online meet for db design | 4 |  | Schema design | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 15 |  | Research Existing Forms and Portals | 9 |  | Hostel Schema | 9 |  | Hostel Schema | 14 |  | UML Refinement | 14 |  | UML Refinement

## Sheet6
TASK ID | TASK DESCRIPTION
1 | Onboarding Setup
2 | Logging Setup
3 | Project Understanding
4 | Faculty Discussion
5 | Faculty Schema
6 | Admin Discussion
7 | Admin Schema
8 | Hostel Discussion
9 | Hostel Schema
10 | Module Reallocation
11 | Students Planning
12 | Students Work
13 | Auth Development
14 | UML Refinement
15 | Research Existing Forms and Portals